## Sheet1
INFORMATION ITEM: | [5 empty] | Attachment B
Clarion University
Information Items for July 16, 2015 Council of Trustees' Meeting
Status of Facilities Projects
| Project |  | Fund Source |  |  | Project Completion Date
Building |  | Number |  | Amount | Status
CLARION
Becht Hall | Renovation | CL-698 | CA | 14300000 | UC | Summer-2015
|  | CL-698 | E&G | 2100000 | UC
| Project Total |  |  | 16400000
Tippin Gym | Renovation/Construction | CL-696 | CA | 41900000 | RB | May-2018
Recreational Pool | Construction | CL-696 | AX | 4200000 | RB | July-2017
| Project Total |  |  | 46100000
Both Campuses | Accessibility Improvements | CL-759 | DM | 70000 | P | Sept-2015
Carlson Library | Masonry Repairs | CL-757 | DM | 100000 | B | Aug-2015
Marwick-Boyd | Fire Curtain & Improvements | CL-770 | DM | 280000 | B | Oct-2015
Nursing at Ralston | New BSN Program | CL-768 | AX | 1500000 | UC | Aug-2015
ADA Improvements | Improve Accessibility | CL-775 | CA | 5000000 | P | Sept-2016
Gemmell Student Center | Interior Design | CL-766 | AX | 1000000 | ID | Sept-2016
Campus Electrical Upgrade | Upgrade for Additional Load | CL774 | DM | 330000 | B | Sept-2015
Steam Tunnel Repair | Rebuild Steam Tunnel Section |  | DM | 152000 | B | Sept-2015
VENANGO
Venango Campus | Pond Dredging | CL-749 | DM | 155000 | UC | Summer-2016
Source of Funds |  | Status
EG = Education & General Funds |  |  |  | P = Planning
AX = Auxiliary |  |  |  | ID = In Design
DM = Deferred Maintenance |  |  |  | B = Bidding/Contracting
CA = Capital Appropriation |  |  |  | UC = Under Construction
G = Grants |  |  |  | C = Complete
SA = Student Assessment |  |  |  | AF = Awaiting Funds
SR = Special Revenue (e.g., Parking Fees, etc.) |  |  |  | AS = Awaiting Scheduling
CL = Cancelled |  |  |  | RB = Rebid